## Aditya task list
Aditya: tasks to implement (iTarang CRM Status, 15 Oct 2026)
14 items. Sorted by priority, then target live date. Yellow columns are for tracking.
# | ID | Priority | Area | Task | Status (15 Oct check) | What to build next | How business will check it | Waiting on | Size | Target live | Report / screen places still to change | Done? (Y/N) | Notes
1 | 11 | P0 | Numbers: metric rules, daily emails, analyses | Report filters: City, SPOC, Type of business (Buyback / Battery Sale / Finance) | Partly built (live, 13 Oct) | 1. Finance is retired: take it out of the import error text, read 'finance' in old links as Battery sale, add the business-type rule to the AI Analyst (tab Report impact). | 1. Open an old link with Type of business = Finance: it shows Battery sale leads, with no error. | Nothing: ready to build | S (1-3 h) | Sat 17 Oct | 1 | Y — done 16 Oct (fbc4f211)
2 | 85 | P0 | Numbers: metric rules, daily emails, analyses | Time limits as admin settings, dated when they take effect | Built differently from the decision (live, 15 Oct) | 1. 15 Oct check: built differently from the decision. Rework: Decision 4: the holiday list is on the Time limits page; there is no separate Admin > Settings > Holidays tab. ¦ Dated limits: the new 'Waiting for a field visit' period comparison judges past periods by today's limit, not the limit in force then. ¦ Decision 6 (every limit an Admin setting): the weekly idle email and the CEO 'Idle leads' column use a fixed 7 days instead of the Admin idle settings. 2. Still missing (15 Oct): Still no limit for a Hot lead to get an owner (9 office hours); 'Sales-ready lead waiting for an owner' is still one 7-calendar-day limit. ¦ Still no fresh 4-hour clock when a lead turns Hot. ¦ Retry limits and the CEO quote-approval limit (4 working hours) are still not settings and are not measured. ¦ Report places: of the 13 Oct examples, the Admin 'Avg time to first touch', the weekly idle email (fixed 7 and 14 days), the daily Sales email boxes and labels such as 'ISR over 5, ASM over 7' are unchanged. Only the field-visit page and the idle screens moved. Check first: about the rest of the 32 without the report list. 3. Live (b27f4e5e, E-337): Admin > Settings > Time limits (16 dated limits, change log, CEO reads); office calendar; lead, owner and field-visit clocks, back-filled; Response time card; daily email totals; Leads download clock columns; 'Limit passed' in Lead events. 4. Missing: Hot Ready to Assigned 9 office hours; a fresh 4-hour Hot owner clock when a lead turns Hot; retry limit; the 4-hour CEO quote approval limit. 5. A missed lead-clock limit is charged to today's owner, not the owner at the time; misses before 10 Sep with inferred owners must stay out of per-person counts. 6. 'Limit passed' records: keep them as fixed records on the day (not rebuilt hourly), add the timeline entry on the lead and a 'Past a limit' chip in the ISR and ASM queues. 7. Log holiday changes, and adding a past holiday must not change past results. 8. About 18 of the 32 report places are untouched (tab Report impact): weekly Idle email, the daily email's Right now, per-person blocks and Oldest overdue, Visits and Quotes downloads, ASM handoff report, Admin 'Avg time to first touch', fixed labels. | 1. Admin changes the Hot limit with a reason and date: the CEO sees it in the log. 2. A Hot lead reaching its owner at 18:00 Saturday is due by 13:00 Monday (office hours). | Nothing: ready to build | M (half to 1 day) | Sat 17 Oct | 22 (shared 85+86) | Y — 50272828 holidays on Time limits page; rest 8f4a6698
3 | 130 | P0 | Outside-system checks & scheduled jobs | Security protections are built but switched off: login gate only logs, webhooks accept unsigned calls, some scheduled jobs don't fail safe | Partly built (live, 15 Oct) | 1. Still missing (15 Oct): NBFC systems with their own code can still send unsigned results until the strict setting is on. 2. Mon 12 Oct: set BOLNA_WEBHOOK_SECRET, DIGIO_WEBHOOK_SECRET and the Bolna tools secret on the live server; confirm each provider sends its signature. Leegality: add a signature check, or switch its webhook off if unused. WHATSAPP_WEBHOOK_INSECURE only off the live site. 3. Make every webhook and scheduled-job check refuse when its secret is missing, and alert; fix the ~15 older job checks to compare the secret safely. 4. Mon 12 - Tue 13 Oct: read the '[api-gate] would refuse' log lines; add any genuine outside caller to the public list (src/lib/security/publicApi.ts). 5. Wed 14 Oct: set API_AUTH_GATE=enforce and WEBHOOK_AUTH_STRICT=1 on the live server; watch the log for an hour. Way back: set API_AUTH_GATE=report. | 1. Logged out, a request to a CRM data address gets 'Unauthorized'. 2. A fake 'agreement signed' message without the code is refused; real Bolna and Digio messages still arrive. | Nothing: ready to build | XS (under 1 h) | Sat 17 Oct | 0 | Y (code) — env switch-on on prod = runbook §3
4 | 86 | P0 | Numbers: metric rules, daily emails, analyses | Lead clock, owner clock and 'Limit passed' events | Partly built (live, 15 Oct) | 1. Still missing (15 Oct): The daily email still shows company totals only: no clock columns per ISR or ASM, and missed limits are not listed under 'Oldest overdue'. ¦ A missed lead-clock limit is still charged to whoever owns the lead now, not to the owner at the moment it was missed. ¦ Misses before 10 Sep with inferred owners still count in per-person figures; the download now flags them, but nothing leaves them out. ¦ 'Limit passed' still does not show on the lead's own timeline, and the reps' queues have no 'Past a limit' chip. 2. See ID 85 (one piece). Biggest gaps: per-person clock columns and 'Limit passed' in the daily email; misses charged to the owner at the time. + 22 report / dashboard places still to change: tab Report impact. | 1. The daily email shows each ISR's median owner clock and limits passed. | Nothing: ready to build | M (half to 1 day) | Mon 19 Oct | 22 (shared 85+86) | Y — 8f4a6698
5 | 5 | P1 | Accounts, invoices & revenue | Converted leads: move to 'Transaction Done'; nudge sales every 10 days; dealer ageing from last order (0-20 Cold, 20-30 Warm, >30 Hot) | Partly built | 1. Nothing new in this row: what is left is ID 70 (the Zoho copy, so old dealers stop showing 'Never ordered') and ID 148 (closed dealers out of the live counts). 2. Confirm the health buckets with Anirudh: Active up to 20 days since the last order, Cooling 21-30, Orange 31-45, Red 46-60, Dormant after 60. | 1. Press 'Order placed' on a dealer: ageing pauses for 15 days; close a dealer as lost: it leaves Dormant. | Nothing: ready to build | XS (under 1 h) | Sat 17 Oct | 0 | Y — no code; buckets to confirm with Anirudh
6 | 70 | P1 | Accounts, invoices & revenue | One-time Zoho backfill: customer GSTIN and invoice line items | Partly built (live, 15 Oct) | 1. Still missing (15 Oct): Not run on the live CRM yet. The 13 Oct note says it has never run there, and nothing since records a run. ¦ Decision 3 (run after products on copied lines are fixed): those fixes are in the code (12 and 14 Oct), so nothing in the code blocks the run any more; someone has to run it. ¦ The Zoho login still cannot read contacts, so customers with no GSTIN on any of their invoices stay unmatched (the copy leaves them to retry later). + 2 report / dashboard places still to change: tab Report impact. | 1. Dealer Health: find a long-standing dealer who ordered only in the Zoho period; until the copy runs on live they still show 'Never ordered'. 2. Developer check: on the live database confirm the Zoho copy's read markers have rows (the 13 Oct note says 0 invoices copied on live). | Nothing: ready to build | XS (under 1 h) | Sat 17 Oct | 2 | N — code ready; prod run = runbook §4
7 | 71 | P1 | Accounts, invoices & revenue | Cancelled invoices keep counting; credit notes not handled | Partly built (live, 15 Oct) | 1. Still missing (15 Oct): Credit notes read before 13 Oct need the developer's fill-in run for their items; until then they lower revenue but not the gross margin rupee figure or batteries sold. Nothing records that run. ¦ Finance still cannot mark a Drive folder as 'Credit notes'; only Admin and Sales Head can, on the Expense tracker screen. ¦ Switching an existing folder to 'Credit notes' still keeps its old 'sale' name filter, so its files may be skipped; adding the folder fresh works. 2. Credit notes get item lines, so batteries sold, Invoice Ledger › By SKU and gross margin ₹ and % take them off; until then fix the CEO Batteries page text. 3. A credit note is not an order: leave it out of order counts, last order, health bucket, reorder reminders and Order placed. 4. List credit notes on the Invoices tab so they can be voided; 22 places in tab Report impact. 5. A credit note also reduces 'Money owed to us' (Kartik, 10 Oct). | 1. Enter a credit note for 2 batteries: the month's batteries sold, By SKU and gross margin all drop by them. | Nothing: ready to build | S (1-3 h) | Mon 19 Oct | 8 | Y — ece7e47a
8 | 167 | P1 | AI Analyst & Feature Requests | AI Analyst: hide free-text fields from Gemini, switch off outside databases, keep uploads for CEO and Admin | Partly built (live, 13 Oct) | 1. Withhold the person and free-text columns in tab Report impact ; mask the customer loan files and Ecofy tables: name → 'Customer #<id>' (same code every time), phone, ID and loan account numbers removed, address → city only (Apoorv, via Kartik 10 Oct); re-run the read-only login on every database and record it. 2. Remove the 'Other database' tab, delete saved outside connections, and refuse them when asking. 3. Reword the iTarang database tab: personal data, notes and call summaries are withheld. 4. Google Sheets / Drive tab: on hold, leave it (Kartik, 10 Oct). | 1. Ask the Analyst for a dealer's notes or a customer's vehicle number: it can't answer. | Nothing: ready to build | M (half to 1 day) | Tue 20 Oct | 16 | Y (code) 8647c707 — prod role + cleanup = runbook §6/§9
9 | 185 | P1 | Numbers: metric rules, daily emails, analyses | Visits = Fresh + Repeat on the rep's basis, plus 'of which new to iTarang'; definitions on the card; click to see the dealers | Decided 14-15 Oct, not started | Visits = Fresh + Repeat on the rep's basis, plus 'of which new to iTarang'; definitions on the card; click to see the dealers + 8 report / dashboard places still to change: tab Report impact. |  | Nothing: ready to build | M (half to 1 day) | Tue 20 Oct | 13 | Y — 5c69c244
10 | 190 | P1 | Numbers: metric rules, daily emails, analyses | 'Waiting for a field visit': follow the date filter and compare periods (pending at start, new, visited, closed without visit, still waiting, % visited) | Built differently from the decision (live, 15 Oct) | 1. Moved to Aditya on 15 Oct (rebalance; Rushikesh built the first version on 14 Oct). 2. 15 Oct check: built differently from the decision. Rework: The card's main number is leads past the limit, with the total waiting as a small line; the decision is 'still waiting' as the number with 'x past the limit' underneath. ¦ Ageing buckets were added (within the limit, up to 7, 14, 30 and over 30 days); the decision says no ageing buckets. ¦ 'Left the queue without a visit' counts any move out of 'Transferred to ASM' without a visit, not only 'visit not needed', handed back to the ISR, or Lost. ¦ A lead moved straight from one ASM to another is not counted as new in the period; the decision counts every lead transferred to an ASM in the period. 3. Still missing (15 Oct): No table per ASM and no team subtotals; the comparison is one total (the page's state, person and team filters do narrow it). ¦ 'Visited' is not split into 'of the old backlog' and 'of the new'. ¦ No '% visited' (visited out of pending + new); it shows '% visited within the limit' instead. ¦ Numbers in the comparison do not open lead lists and have no download; only the existing past-the-limit list has a download. + 6 report / dashboard places still to change: tab Report impact. | 1. Open the Sales dashboard: the big number on 'Waiting for a field visit' is only the leads past the limit, with 'N waiting in all' in small text. 2. Click it, set Period A 1-7 Oct and Period B 8-14 Oct and press Compare: you get one company-wide column per period, no rows per ASM. 3. Click a number in the comparison table: nothing opens. | Nothing: ready to build | M (half to 1 day) | Wed 21 Oct | 9 | Y — 551f184f
11 | 192 | P1 | Numbers: metric rules, daily emails, analyses | Idle leads (Needs Attention and every idle count) ignore the follow-up date, and a reassigned lead inherits the old owner's idle days | Built differently from the decision (live, 15 Oct) | 1. Weekly idle email: 5 working days for ISRs, 7 for ASMs (from Admin > Time limits), same as the page; today it is 7 (and 14) for everyone (digests/kinds/idle-weekly.ts). 2. Leads list Idle column and Idle filters, and the CEO People table 'Idle leads': same rule as Needs Attention (latest of last action, the date the holder got the lead, a follow-up within 30 days). 3. Needs Attention: show the follow-up date on each row. 4. Keep: a follow-up more than 30 days away is ignored (Kartik, 15 Oct). + 14 report / dashboard places still to change: tab Report impact. | 1. A lead with a follow-up next week is on no idle list and not in the weekly email. 2. Reassign a lead today: the Leads list Idle column shows 0 for the new holder. 3. A lead with a follow-up in 60 days shows on Needs Attention with that date on the row. | Nothing: ready to build | S (1-3 h) | Wed 21 Oct | 17 | Y — e05021ef
12 | 194 | P1 | Numbers: metric rules, daily emails, analyses | 'My day' email to every ISR and ASM (their own numbers and work list; managers also get their team) | Decided 14-15 Oct, not started | 1. New digest kind 'my_day': one email per active ISR / ASM (users with an email), 09:00 Mon-Sat; Admin switch per role. Reuse the daily Sales builder scoped to the person (+ direct reports for managers). 2. Sections: my numbers (yesterday, MTD, target to date vs actual), my work list with lead links, my team table with subtotal (managers only). No company totals, no other teams, no ranking. 3. Numbers must equal the person's row in the management email and their Performance page. + 5 report / dashboard places still to change: tab Report impact. | 1. Sonu's email: his row equals his row in the management email; the team subtotal equals his team subtotal there. | Nothing: ready to build | M (half to 1 day) | Wed 21 Oct | 8 | Y (code) 52adcdcd — E-353 + switch-on on prod = runbook §9
13 | 188 | P1 | Numbers: metric rules, daily emails, analyses | Daily Sales email in the Sales Head's format (Anirudh to review the current one and share changes) | Decided 14-15 Oct, not started | Daily Sales email in the Sales Head's format (Anirudh to review the current one and share changes) |  | Decision: Anirudh | M (half to 1 day) | After the decision | 0 | N — waiting on Anirudh
14 | 184 | P2 | Numbers: metric rules, daily emails, analyses | One 'Ready leads with no owner' card with an AI / Hot / Other split, and the Leads export giving the same count | Built differently from the decision (live, 15 Oct) | 1. Moved to Aditya on 15 Oct (rebalance; Rushikesh built the first version on 14 Oct). 2. 15 Oct check: built differently from the decision. Rework: The split is AI qualified / created by a rep / other, not AI / Hot / Other. Hot is shown as an extra number that overlaps the others, so a lead that is AI qualified and Hot is counted twice in the line. 3. Still missing (15 Oct): The card is not renamed; it still says 'Sales-ready leads with no owner'. ¦ The CEO card, Ready to Assign and the daily email 'Right now' line did not get the new name or split. ¦ No 'Ready, no owner' filter on the Leads list or its export, so the export cannot yet be matched to the card. + 11 report / dashboard places still to change: tab Report impact. | 1. Open the Sales dashboard and read the line under 'Sales-ready leads with no owner': it says AI qualified / created by a rep / other, then a separate Hot count. 2. Click the card: Ready to Assign opens; its count should match the card. 3. Open Leads: there is no 'Ready, no owner' filter yet. | Nothing: ready to build | S (1-3 h) | Thu 22 Oct | 14 | Y — 9dbf4bf9 (+ tile in 551f184f)
Orange 'Waiting on' = blocked on a business decision (not on Aditya). Source: tab 'Aditya' (rows marked Next), cross-checked with tab 'Dev view'.